## Slide 1
FORESTRY
RM 8 bil in exports by 2030
MUDeNR Outcome:
Increase Timber & Non Wood Forest Products Exports Earnings
Community-Based Ecotourism and conservation Totally Protected Area
Certify Long Term Forest License Area and Forest Plantation
200,000 ha degraded area (100%) planted/restored by 2030
Obtain world recognition for sustainable management practices and conservation effort
H2-2025
Program
H2-2025 Target
Rating
H2-2025 Status
program test 1
N/A
N/A
q3 delayed
acbcbcbc
N/A
Timber Export Value (RM)
'24 Total
RM 2,128,434,989
'25 Total
RM 0.00
Chart: 
| January | February | March | April | May | June | July | August | September | October | November | December
2024 | 276004972.69 | 191530929.47 | 214907671.7 | 232014272.14 | 324627750.87 | 212303812.34 | 274788036.68 | 210420404.31 | 191837139
2025
TPA Protection & Biodiversity Conservation Programs
70
On-going programs and initiatives by SFC (as of December 2024)
Certification of FMU & FPMU
56.8
%
1,705,761 ha FMU Certified (as of June 2025)
72.2
%
128,601 ha FPMU Certified (as of June 2025)
Obtain world recognition for sustainable management practices and conservation effort
100
%
SDGP UNESCO Global Geopark(as of June 2025)
100
%
Lambir Hill NP and Bako NP inscribed as ASEAN Heritage Park(as of June 2025)
Legend:
Monthly target achieved, Project on track
Miss in target but still on track for 2025
Severe delays
Not started
2024
2025
DRAFT 30 Jul 2025
'25 Total
323.60
'24 Total
30,380.02
Total Degraded Area (Ha)
Chart: 
| January | February | March | April | May | June | July | August | September | October | November | December
2025 | 5.6 | 86.5 | 62.2 | 127.3 | 42
2024 | 3572.12 | 6911.42 | 3565.31 | 2243.09 | 3190.19 | 3618.48 | 1378.09 | 1536.83 | 1141.79 | 1311.2 | 942.5 | 969